## Pilot Gantt Chart
Activity / Task | June (M1) | July (M2) | August (M3) | September (M4) | October (M5) | November (M6)
Engineer 1: Central UAT Test Case Identification & Migration
Discovery, Analysis & Planning
1. Deep Dive into Existing UAT Processes & Test Assets
2. Identify & Prioritize UAT Scenarios for Automation
3. Master BDD Tooling & Methodology
Migration, Automation Development & Initial Integration
4. Convert Selected UAT Scenarios to BDD (Gherkin)
5. Develop Automated Test Scripts using Playwright
6. Setup & Test Execution in DT2 Environment
Refinement, Reporting & Knowledge Transfer Preparation
7. Iterate and Refine Automated UAT Suite
8. Establish Automated UAT Reporting
9. Document Best Practices & Create Migration Playbook
10. Prepare for Knowledge Sharing & Team Onboarding
Engineer 2: Embedding New Ways of Working & Engineering Practices
Assessment, Strategy Definition & Foundational Setup
1. Baseline Current Engineering Practices & CI/CD Maturity
2. Develop & Communicate Pilot Engineering Practices Adoption Strategy
3. Tooling Onboarding & Environment Preparation
Implementation, Coaching & CI/CD Integration
4. Drive Adoption of Unit Testing & Developer-Led Testing
5. Integrate Automated Tests into CI/CD Pipelines (GitHub Actions Focus)
6. Establish & Champion Mocking Practices (Mockito/MockFlow)
Optimization, Standardization & Knowledge Dissemination
7. Refine CI/CD Pipelines (GitHub Actions) and Test Execution Efficiency
8. Develop & Document Standardized Engineering Playbooks
9. Facilitate Performance Profiling Setup
10. Prepare for Scaling & Knowledge Transfer