## Pilot Gantt (Sprints)
Activity / Task (Est. Timeline) | Sprint 1 (W1-W2) | Sprint 2 (W3-W4) | Sprint 3 (W5-W6) | Sprint 4 (W7-W8) | Sprint 5 (W9-W10) | Sprint 6 (W11-W12) | Sprint 7 (W13-W14) | Sprint 8 (W15-W16) | Sprint 9 (W17-W18) | Sprint 10 (W19-W20) | Sprint 11 (W21-W22) | Sprint 12 (W23-W24)
Engineer 1: Central UAT Test Case Identification & Migration
Phase 1: Discovery, Analysis & Planning (Est. Months 1-2)
1. Deep Dive into Existing UAT Processes & Test Assets (W1-W3)
2. Identify & Prioritize UAT Scenarios for Automation (W3-W6)
3. Master BDD Tooling & Methodology (W2-W5)
Phase 2: Migration, Automation Development & Initial Integration (Est. Months 3-4)
4. Convert Selected UAT Scenarios to BDD (Gherkin) (W7-W10)
5. Develop Automated Test Scripts using Playwright (W9-W16)
6. Setup & Test Execution in DT2 Environment (W15-W18)
Phase 3: Refinement, Reporting & Knowledge Transfer Preparation (Est. Months 5-6)
7. Iterate and Refine Automated UAT Suite (W17-W24)
8. Establish Automated UAT Reporting (W19-W22)
9. Document Best Practices & Create Migration Playbook (W20-W24)
10. Prepare for Knowledge Sharing & Team Onboarding (W22-W24)
Engineer 2: Embedding New Ways of Working & Engineering Practices
Phase 1: Assessment, Strategy Definition & Foundational Setup (Est. Months 1-2)
1. Baseline Current Engineering Practices & CI/CD Maturity (W1-W3)
2. Develop & Communicate Pilot Engineering Practices Adoption Strategy (W2-W4)
3. Tooling Onboarding & Environment Preparation (W3-W6)
Phase 2: Implementation, Coaching & CI/CD Integration (Est. Months 3-4)
4. Drive Adoption of Unit Testing & Developer-Led Testing (W7-W16)
5. Integrate Automated Tests into CI/CD Pipelines (GitHub Actions Focus) (W9-W16)
6. Establish & Champion Mocking Practices (Mockito/MockFlow) (W10-W15)
Phase 3: Optimization, Standardization & Knowledge Dissemination (Est. Months 5-6)
7. Refine CI/CD Pipelines (GitHub Actions) and Test Execution Efficiency (W17-W24)
8. Develop & Document Standardized Engineering Playbooks (W18-W24)
9. Facilitate Performance Profiling Setup (W20-W23)
10. Prepare for Scaling & Knowledge Transfer (W22-W24)