## Pilot Gantt (Sprints)
Activity / Task (Est. Timeline) | Sprint 1 (W1-2) | Sprint 2 (W3-4) | Sprint 3 (W5-6) | Sprint 4 (W7-8) | Sprint 5 (W9-10) | Sprint 6 (W11-12) | Sprint 7 (W13-14) | Sprint 8 (W15-16) | Sprint 9 (W17-18) | Sprint 10 (W19-20) | Sprint 11 (W21-22) | Sprint 12 (W23-24)
Engineer 1: Central UAT Test Case Identification & Migration
Discovery, Analysis & Planning
1. Deep Dive into Existing UAT Processes & Test Assets
2. Identify & Prioritize UAT Scenarios for Automation
3. Master BDD Tooling & Methodology
Migration, Automation Development & Initial Integration
4. Convert Selected UAT Scenarios to BDD (Gherkin)
5. Develop Automated Test Scripts using Playwright
6. Setup & Test Execution in DT2 Environment
Refinement, Reporting & Knowledge Transfer Preparation
7. Iterate and Refine Automated UAT Suite
8. Establish Automated UAT Reporting
9. Document Best Practices & Create Migration Playbook
10. Prepare for Knowledge Sharing & Team Onboarding
Engineer 2: Embedding New Ways of Working & Engineering Practices
Assessment, Strategy Definition & Foundational Setup
1. Baseline Current Engineering Practices & CI/CD Maturity
2. Develop & Communicate Pilot Engineering Practices Adoption Strategy
3. Tooling Onboarding & Environment Preparation
Implementation, Coaching & CI/CD Integration
4. Drive Adoption of Unit Testing & Developer-Led Testing
5. Integrate Automated Tests into CI/CD Pipelines (GitHub Actions Focus)
6. Establish & Champion Mocking Practices (Mockito/MockFlow)
Optimization, Standardization & Knowledge Dissemination
7. Refine CI/CD Pipelines (GitHub Actions) and Test Execution Efficiency
8. Develop & Document Standardized Engineering Playbooks (W18-W24)
9. Facilitate Performance Profiling Setup
10. Prepare for Scaling & Knowledge Transfer